## Application
CONTRACTOR's INTERIM PAYMENT APPLICATION |  |  |  |  | ENGINEER'S CERTIFICATE NO. 01
Project Name | : REHABILITATION OF THE A-017 ROAD |  | Statement No | : 03
CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
| SECTION FROM CH. 112+600 KM TO CH. 118+600 KM |  | Valuation Period Ending | : 31st December 2022
Contract No: | : RDA/MFAP/ICB/OFID-04(A) |  | Submission Date | : 10th January 2022
Employer | : Road Development Authority |  | Commencement Date | : 17th October 2022
Engineer | : |  | Contract Price | : Rs. 1,825,518,210.94
Contractor | : Consulting Engineers & Contractors (Pvt) Ltd. |  | Minimum Amount of IPC | : Rs. 54,765,546.33
Payment A/C No. | : 004100630000738 |  | Limit of Retention | : Rs. 91,275,910.55 | 91275910.55
[5 empty] | 2022-09-06 | 2022-10-04
1. Amount of Advance Payment paid to the Contractor (Clause 14.2 of PCC ) |  |  |  | 0
2. Value of Works executed and all other matters payable (Sub Clause 14.3(a) & (f) GCC |  |  |  | #REF!
and Sub Clause 13.7 -GCC but not including Item 3 and 7 below.
3. ADD/DEDUCT Contract Price Fluctuation |  | (Clause 13.8 of PCC) |  | #REF!
4. Value of Works after Contract Price Fluctuation [2+3] |  |  |  | #REF!
5. DEDUCT Retention Money @ 10% (Sub Clause 14.2(d) PCC[ Limit : 5% of Contract Price]) |  |  |  | #REF!
6. NET Valuation [4-5] |  |  |  | #REF!
7. ADD 80% of Materials on Site [Sub Clause14.5(c)(1) GCC ] |  |  |  | 0
8. Gross Valuation [6+7] |  |  |  | #REF!
1047101654.003
9. DEDUCT Cumulative Gross Value of Paid previous Interim Certificate 14.3(g)-GCC |  |  |  | #REF!
10. Gross Amount of this Interim Certificate [8-9] |  |  |  | #REF!
11. Release of Retention Money [Sub Clause (14.9)] |  |  |  | 0
12. DEDUCT Recovery of Advance Payment [Sub Clause 14.2(d) PCC] |  |  |  | 0
13. NET AMOUNT of this Interim Certificate after release of |  |  |  | #REF! | 110581924.74
Retention money and recovery of advance payment [10+11-12]
14. Value Added Tax [15%] |  |  |  | #REF! | 0
15. AMOUNT FOR PAYMENT FOR THIS CERTIFICATE [13 + 14] |  |  |  | #REF! | 568043871.33
16. Previous cumulative recovery of Advance payment |  |  |  | 0 | 0
17. Recovery of Advance payment from this IPC |  |  |  | 0
18. Balance of Advance Payment to be recovered [1-(16+17)] |  |  |  | 0
Prepared By |  |  |  | Submitted by
J Garusinghe |  |  |  | WA Premarathna
Quantity Surveyor |  |  |  | Project Manager

## GS
:MISCELLANEOUS FOREIGN AIDED PROJECT
REHABILITATION OF THE A-017 ROAD CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
FUNDED BY OPEC FUND FOR INTERNATIONAL DEVELOPMENT (OFID)
SECTION FROM CH. 112+600 KM TO CH. 118+600 KM
:RDA/MFAP/ICB/OFID-04(A)
SUMMARY SHEET
AMOUNT ( Sri Lanka Rupees)
Bill No. | Description | Allot. % | Contract
1 | Preliminary and General | 7.75% | 141519140.93
2 | Site Clearing | 4.33% | 79000093.68
3 | Earthworks | 25.05% | 457209997.91
4 | Road Pavement | 12.13% | 221349309.06
5 | Drainage | 3.37% | 61543114.3
6 | Culvert, Retaining Structures | 22.27% | 406494470.59
7 | Incidental Construction | 2.92% | 53339166.44
8-1 | Day Works - Labour | 0.04% | 805454.7
8-2 | Day Works - Equipment | 0.07% | 1368785.88
8-3 | Day Works - Materials | 0.1% | 1785035.26
9 | Provisional Sums | 1.97% | 36000000
SUB - Total 1 :(Excl. Provisional Sums) |  | 78.03% | 1424414568.75
SUB - Total 2 :Provisional Sums |  | 1.97% | 36000000
A | TOTAL BOQ AMOUNT | 80% | 1460414568.75
B | Variation Orders | 0% | 0
C | Claims | 0% | 0
D | Construction Cost Total (A+B+C) | 80% | 1460414568.75
E | Physical Contingencies at 10% of SUB (1 + 2) | 8% | 146041456.88
F | Financial Contingencies at 15% of SUB (1 + 2) | 12% | 219062185.31
SUB - Total 3:Total Project Cost (D+E+F) without VAT |  | 100% | 1825518210.94
Value Added Tax 15% (For the Contract Amount) and 0% (For the Contract Price) of Sub Total 03 |  | 15% | 273827731.64
Total Project cost with VAT |  | 115% | 2099345942.58

## Mat @ Site (2) (hidden)
REHABILITATION AND IMPROVEMENT TO PERADENIYA-BADULLA-CHENKALADY ROAD FROM PADIYATHALAWA TO THAMPITIYA (219+800 KM - 249+800 KM) OF BADULLA CHENKALADI ROAD IMPROVEMENT PROJECT
[5 empty] | CONTRACT PACKAGE: RDA/BCRIP/ICB/SFD/02 | [5 empty] | Annex : |  | E
Employer |  | : Road Development Authority | [6 empty] | Interim Payment Application : |  |  |  | No. 35
Consultant |  | : Resources Development Consultants (Pvt) Ltd | [6 empty] | Period Ending : |  |  |  | 31st May 2021
Contractor |  | : Consulting Engineers & Contractor (Pvt) Ltd | [6 empty] | Sub Clause : |  |  |  | 14.5 (c) (i)
Material at Site
S/N | Description |  |  |  |  | Unit |  | Quantity | Rate |  | Amount | Remarks
1 | Cement (50kg) |  |  |  |  | Bags |  | 0 | 15055.23 |  | 0
2 | Bitumen
| MC30 |  |  |  |  | ltr |  | 0 |  |  | 0
| Bitumen CRS1 |  |  |  |  | ltr |  | 0 |  |  | 0
| Bitumen CSS1 |  |  |  |  | ltr |  | 0 |  |  | 0
3 | Reinforcement Steel
| 10 mm (12m) |  |  |  |  | Tonne |  | 0 |  |  | 0 | [5 empty] | 1443 | 0 | 0.617 | 12 | 0
| 12 mm (6m) |  |  |  |  | Tonne |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 0.889 | 6 | 0
| 12 mm (12m) |  |  |  |  | Tonne |  | 0 |  |  | 0 | [5 empty] | 318 | 0 | 0.889 | 12 | 0
| 16 mm (6m) |  |  |  |  | Tonne |  | 0 |  |  | 0 | [5 empty] | 269 | 0 | 1.58 | 6 | 0
| 16 mm (12m) |  |  |  |  | Tonne |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 1.58 | 12 | 0
| 20 mm (12m) |  |  |  |  | Tonne |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 2.469 | 12 | 0
| 25 mm (12m) |  |  |  |  | Tonne |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 3.858 | 12 | 0
| 6 mm(Mild Steel) |  |  |  |  | Tonne |  | 0 |  |  | 0 |  |  |  |  | kg | 21 | 0 |  |  | 0
| 10 mm(6 m-Mild Steel) |  |  |  |  | Tonne |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 0.617 | 6 | 0
| 16 mm(6 m-Mild Steel) |  |  |  |  | Tonne |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 1.58 | 6 | 0
| 20 mm(6 m-Mild Steel) |  |  |  |  | Tonne |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 2.469 | 6 | 0
| 20 mm(12 m-Mild Steel) |  |  |  |  | Tonne |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 2.469 | 12 | 0
| 25 mm(6 m-Mild Steel) |  |  |  |  | Tonne |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 3.858 | 6 | 0
[17 empty] | 0 | 0
4 | Metal (Aggregate 19 mm) |  |  |  |  | Cu.m |  | 0 |  |  | 0 | [7 empty] | 2.83 |  | 0
5 | Geotextiles |  |  |  |  | sq.m |  | 0 |  |  | 0
6 | Aggregates (ABC) |  |  |  |  | Cu.m |  | 0 |  |  | 0 |  |  | 1893.31 | 4876.13 |  | 6297.64 | 0 |  |  | 0
[14 empty] | 3874.25 |  |  |  | 0
7 | Sand |  |  |  |  | Cu.m |  | 0 |  |  | 0 |  |  | -1980.94 | 0 |  |  | 0 | 2.83 |  | 0
8 | Precast Units - Bridge Beams
[6 empty] | Nos |  | 0 |  |  | 0
9 | Rubble |  |  |  |  | Cu.m |  | 0 | 0 |  | 0 | [7 empty] | 2.83 |  | 0
10 | Road Studs & Road Marking Material |  |  |  |  | Nos |  | 0 | 0 |  | 0
11 | Gabion Boxes |  |  |  |  | Nos |  | 0 | 0 |  | 0
Sub Total | [10 empty] | 0 |  |  | 25455255.8 | 25455255.8 |  |  |  | 21412465.2 | -21412465.2 |  | 3230.6
Total Carried Forward (Sub Total x 80%) | [10 empty] | 0 |  |  | 20364204.64 | 20364204.64 |  |  |  | 17129972.16 | -17129972.16 |  | 6438.45 | -6438.45
Note :
Prepared By QS (CEC) |  |  |  | Checked By (CEC) |  |  |  | Checked By - (RDC) |  |  | Recommended By - (RDC)
………………………………… |  |  | ……..……………………….. |  |  |  | …………………………………….. |  |  | …….………………………………
Quantity Surveyor |  |  | Project Manager |  |  |  |  | Assistant Resident Engineer |  |  | Quantity Surveyor |  |  |  | 11119812 |  | -11119812
Date: |  |  |  | Date: |  |  |  | Date: |  |  | Date:
5640130.24
5640130.24
3.125

## Bill 1
CONTRACT NAME |  | :MISCELLANEOUS FOREIGN AIDED PROJECT
REHABILITATION OF THE A-017 ROAD CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
FUNDED BY OPEC FUND FOR INTERNATIONAL DEVELOPMENT (OFID)
SECTION FROM CH. 112+600 KM TO CH. 118+600 KM
CONTRACT NO |  | :RDA/MFAP/ICB/OFID-04(A)
BILL No.1 : PRELIMINARY AND GENERAL ITEMS
BOQ
Item |  | Description | Unit | Quantity | Rate | Amount (Rs.)
Bill | Pay
1.1 |  | TRAFFIC SAFETY AND CONTROL
1 | 103(1) | Management, safety & control & Temporary diversion of traffic including provision of a general traffic management plan | mth | 24 | 664201.22 | 15940829.28 | 22140.04
1.2 |  | CONTRACTOR'S SITE ESTABLISHMENT
1 | 108.(1) | Mobilization of contractor's facilities and plant / machinery | LS | 1 | 26568048.99 | 26568048.99
2 | 108.(2) | De-mobilization of contractor's facilities and plant / machinery | LS | 1 | 885601.63 | 885601.63
1.3 |  | SETTING OUT, CROSS SECTION SURVEYS AND DRAWINGS
1 | 117(1) | All necessary surveying, levelling and setting outs including establishment of all control points and monuments | km | 6 | 1328402.45 | 7970414.7
2 | 117(2) | Preparation of detailed cross sections | nr | 600 | 17712.03 | 10627218
1.4 |  | PROJECT SIGN BOARDS
1 | 118(1) | Provide and maintain project signboards | nr | 2 | 265680.49 | 531360.98
1.5 |  | INSURANCE, BONDS AND SECURITIES
1 | 119.1(1) | Insurance of the works | LS | 1 | 6199211.43 | 6199211.43
2 | 119.1(2) | Insurance of the contractor's equipment | LS | 1 | 1771203.27 | 1771203.27
3 | 119.1(3) | Third party insurance | LS | 1 | 885601.63 | 885601.63
4 | 119.1(4) | Workmen's compensation insurance | LS | 1 | 885601.63 | 885601.63
5 | 119.2(1) | Performance security | LS | 1 | 2656804.9 | 2656804.9
6 | 119.2(2) | Bank guarantee for advance payment | LS | 1 | 7084813.06 | 7084813.06
1.6 |  | VEHICLES FOR THE EMPLOYER
1 | 126 (1) | Provide and maintenance of vehicles - Type A | veh-mth | 27 | 442800.82 | 11955622.14 | 14760.03
1.7 |  | MAINTENANCE OF EXISTING ROAD
1 | 121 (1) | Maintenance of road | km-week | 624 | 22140.04 | 13815384.96 | 18976.16
1.8 |  | LABORATORY
1 | 128 (1) | Establishment of Fully furnished Main Laboratory and removal on completion of project. | LS | 1 | 22140040.83 | 22140040.83 | 55876.23
2 | 128 (3) | Maintain Laboratory and Lab equipment | mth | 27 | 265680.49 | 7173373.23
3 | 129 (1) | Provide survey equipment for exclusive use of the Employer / Engineer | LS | 1 | 4428010.27 | 4428010.27
Bill No 01. Total Carried to Summary | [5 empty] | 141519140.93

## Bill 2
CONTRACT NAME |  | :MISCELLANEOUS FOREIGN AIDED PROJECT
REHABILITATION OF THE A-017 ROAD CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
FUNDED BY OPEC FUND FOR INTERNATIONAL DEVELOPMENT (OFID)
SECTION FROM CH. 112+600 KM TO CH. 118+600 KM
CONTRACT NO |  | :RDA/MFAP/ICB/OFID-04(A)
BILL NO 2: SITE CLEARING
BOQ
Item |  | Description | Unit | Quantity | Rate | Amount (Rs.)
Bill | Pay
2.1 |  | CLEARING AND GRUBBING
1 | 201(1) | Clearing and grubbing | sq.m | 26400 | 265.68 | 7013952
2 | 201(3) | Removal of trees, girth greater than or equal to 600 and less than 1200 mm | No. | 1080 | 22140.04 | 23911243.2
3 | 201(4) | Removal of trees, girth greater than or equal to 1200 and less than 2000 mm | No. | 720 | 30996.07 | 22317170.4
4 | 201(5) | Removal of trees, girth greater than 2000 mm. | No. | 480 | 39852.08 | 19128998.4
5 | 201(6) | Removal of stumps of previously felled trees;girth 300-600mm | No. | 60 | 13284.02 | 797041.2
6 | 201(7) | Removal of stumps of previously felled trees;girth 600-1200mm | No. | 54 | 17712.03 | 956449.62
7 | 201(8) | Removal of stumps of previously felled trees;girth 1200-2000mm | No. | 48 | 22140.05 | 1062722.4
8 | 201(9) | Removal of stumps of previously felled trees;girth over 2000mm | No. | 48 | 30996.07 | 1487811.36
9 | 201(10) | Removal of over hanging branches of girth exceeding 300mm. | No. | 90 | 7084.81 | 637632.9
2.2 |  | REMOVAL OF EXISTING STRUCTURES |  |  |  | 0
1 | 202(1) | Dismantaling and removal of brick masonery structure | cu.m | 180 | 3099.61 | 557929.8
2 | 202(2) | Dismantaling and removal of random rubble structure | cu.m | 150 | 3985.21 | 597781.5
3 | 202(3) | Dismantaling and removal of concrete structure | cu.m | 90 | 4428.01 | 398520.9
4 | 202(5) | Remove of fencing | Lm | 150 | 885.6 | 132840
Bill No.2 Total Carried to Summary | [5 empty] | 79000093.68

## Bill 3
CONTRACT NAME |  | :MISCELLANEOUS FOREIGN AIDED PROJECT
REHABILITATION OF THE A-017 ROAD CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
FUNDED BY OPEC FUND FOR INTERNATIONAL DEVELOPMENT (OFID)
SECTION FROM CH. 112+600 KM TO CH. 118+600 KM
CONTRACT NO |  | :RDA/MFAP/ICB/OFID-04(A)
BILL No 03: EARTH WORKS
BOQ
Item |  | Description | Unit | Quantity | Rate | Amount (Rs.)
Bill | Pay
3.1 |  | ROADWAY EXCAVATION
1 | 301(1) | Roadway excavation,soil suitable for fill | cu.m | 4968 | 4428.01 | 21998353.68
2 | 301(2) | Roadway excavation, soft rock | cu.m | 9936 | 3099.61 | 30797724.96
3 | 301(3) | Roadway excavation, hard rock | cu.m | 19872 | 7084.81 | 140789344.32
4 | 301(5) | Roadway excavation, unsuitable soil | cu.m | 55642 | 2036.88 | 113336076.96
5 | 301(7) | Roadway Pavement Excavation. | cu.m | 1075 | 2656.8 | 2856060
6 | 301(8) | Prepare sub grade in cut areas | sq.m | 35789 | 177.12 | 6338947.68
7 | 301(9) | Roadway excavation,marshy soil | cu.m | 4968 | 1594.08 | 7919389.44
8 | 301(5a) | Cutting side drain | cu.m | 3840 | 1771.2 | 6801408
9 | 301(3a) | Roadway excavation, Hard rock blasting prohibited | cu.m | 994 | 26568.05 | 26408641.7
10 | 301(4) | Roadway excavation - Boulder | cu.m | 2981 | 5756.41 | 17159858.21
3.2 |  | EXCAVATION AND BACKFILLING OF STRUCTURES |  |  |  | 0
1 | 302(1) | Excavation for structures,soil suitable for backfill | cu.m | 842 | 2656.8 | 2237025.6
2 | 302(3) | Excavation for structures,boulders | cu.m | 281 | 3542.41 | 995417.21
3 | 302(4) | Excavation for structures,hard rock | cu.m | 842 | 7084.81 | 5965410.02
4 | 302(5) | Excavation for structures, unsuitable soil | cu.m | 1685 | 2656.8 | 4476708
5 | 302(9) | Preparation of base for foundation | LS | 1 | 3542777.45 | 3542777.45
6 | 302(15) | Excavation in unsuitable soil and backfill with approved soil | cu.m | 1685 | 5313.61 | 8953432.85
7 | 302(8) | Backfill with granular materials | cu.m | 281 | 3542.41 | 995417.21
3.3 |  | EMBANKMENT CONSTRUCTION |  |  |  | 0
1 | 304(A) | Remove and replace weak material with buolders | Cum | 250 | 5313.61 | 1328402.5
2 | 304(1a) | Embankment construction using type - 11 material from roadway excavation and compacted in position. | cu.m | 2981 | 2214 | 6599934
3 | 304(1b) | Embankment construction using type - 1 material from roadway excavation and compacted in position. | cu.m | 1987 | 2214 | 4399218
4 | 304(2a) | Embankment construction using borrow material compacted in position Type- 11 material | cu.m | 8640 | 2302.56 | 19894118.4
5 | 304(2b) | Embankment construction using borrow material compacted in position Type- 1 material | cu.m | 7776 | 2302.56 | 17904706.56
6 | 304(3) | Trimming leveling and compaction of original ground | sq.m | 8640 | 177.12 | 1530316.8
7 | 304(4) | Provide and place Geofabric , Filter Fabric | Sq.m. | 432 | 708.48 | 306063.36
8 | 304(6) | Embanment Construction using Rock fill | cu.m | 500 | 5756.41 | 2878205
9 | 801(1) | Top soiling | sq.m | 900 | 354.24 | 318816
10 | 802(1) | Turfing (Assuming Turfing thickness 150mm) | sq.m | 900 | 531.36 | 478224
Bill No.3 Total Carried to Summary | [5 empty] | 457209997.91

## Bill 4
CONTRACT NAME |  | :MISCELLANEOUS FOREIGN AIDED PROJECT
REHABILITATION OF THE A-017 ROAD CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
FUNDED BY OPEC FUND FOR INTERNATIONAL DEVELOPMENT (OFID)
SECTION FROM CH. 112+600 KM TO CH. 118+600 KM
CONTRACT NO |  | :RDA/MFAP/ICB/OFID-04(A)
BILL No 04: ROAD PAVEMENT
BOQ
Item |  | Description | Unit | Quantity | Rate | Amount (Rs.)
Bill | Pay
4.1 |  | SUB BASES, CAPPING LAYERS AND BASES
1 | 401(1) | Provide and place Sub-base as compacted in position Type I (upper sub base) | cu.m | 5040 | 4428.01 | 22317170.4
2 | 405(1) | Dense graded aggregate base (37.5mm) | cu.m | 9990 | 7084.82 | 70777351.8
4.2 |  | RECONSTRUCTION OF EXISTING BASES
1 | 408(1) | Base correction | cu.m | 576 | 6199.21 | 3570744.96
2 | 408(2) | Scarification of existing base | sq.m | 576 | 265.68 | 153031.68
4.3 |  | SHOULDER CONSTRUCTION
1 | 409(1) | Earthen shoulder as compacted in position | cu.m | 2700 | 3985.21 | 10760067
4.4 |  | PRIME COAT AND TACK COAT
1 | 501(5) | Prime coat with bituminous MC30 over DGAB at the rate of 1lt/sqm including application of blotting material | sq.m | 46620 | 221.4 | 10321668
2 | 502(2) | Bituminous tack coat using CRS 1 at rate of 0.25 - 0.55 ltr per sq.m | sq.m | 46620 | 177.12 | 8257334.4
4.5 |  | ASPHALTIC CONCRETE SURFACING
1 | 506(1) | Asphalt Concrete in Wearing Course | tonnes | 5711 | 16383.62 | 93566853.82
2 | 506(3) | Asphalt Concrete in regulating course | tonnes | 100 | 16250.87 | 1625087
Bill No. 4 Carried to Summary | [5 empty] | 221349309.06

## Bill 5
CONTRACT NAME |  | :MISCELLANEOUS FOREIGN AIDED PROJECT
REHABILITATION OF THE A-017 ROAD CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
FUNDED BY OPEC FUND FOR INTERNATIONAL DEVELOPMENT (OFID)
SECTION FROM CH. 112+600 KM TO CH. 118+600 KM
CONTRACT NO |  | :RDA/MFAP/ICB/OFID-04(A)
BILL No.5 : DRAINAGE
BOQ
Item |  | Description | Unit | Quantity | Rate | Amount (Rs.)
Bill | Pay
5.1 |  | ROAD SIDE AND LEADAWAY DRAINS
1 | 302(15) | Excavation for built up drains in unclassified soil & backfilling. | cu.m | 2016 | 3099.61 | 6248813.76
2 | 302(4) | Excavation for leadaway drains, hard rock | cu.m | 100 | 7084.81 | 708481
3 | 701(2a) | Lining of drains with in situ class A or B 25/20 concrete | cum | 1260 | 23911.25 | 30128175
4 | 701(2b) | Lining of drains with in situ class C15/20 concrete | cum | 252 | 20811.65 | 5244535.8
5 | 701(3) | Lining of drains with R.R. masonry | cum | 40 | 13284.01 | 531360.4
6 | 701(6a) | 100mm thick Precast concrete cover slab including reinforcement & formwork | sq.m | 168 | 4428.01 | 743905.68
7 | 701(6b) | 125mm thick Precast concrete cover slab including reinforcement & formwork | sq.m | 202 | 5756.41 | 1162794.82
8 | 701(6c) | 150mm thick Precast concrete cover slab including reinforcement & formwork | sq.m | 336 | 6642.01 | 2231715.36
9 | 701(7) | Supply and fixing of Galvanized steel Gratings as per the given Drawings | sq.m | 100 | 4428.01 | 442801
10 | 1001(2a) | Concrete nominal mix 1:3:6 (37.5mm) as screed to the foundation | cum | 72 | 19483.24 | 1402793.28
11 | 1002(1) | Steel Reinforcement (Tor Steel) | tonne | 10 | 287820.54 | 2878205.4
12 | 1008(2) | Formwork rough finish | sq.m | 2520 | 1948.32 | 4909766.4
13 | 1008(1) | Formwork, smooth finish | sq.m | 2520 | 1948.32 | 4909766.4
Bill No. 5 Carried to Summary | [5 empty] | 61543114.3

## Bill 6
CONTRACT NAME |  | :MISCELLANEOUS FOREIGN AIDED PROJECT
REHABILITATION OF THE A-017 ROAD CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
FUNDED BY OPEC FUND FOR INTERNATIONAL DEVELOPMENT (OFID)
SECTION FROM CH. 112+600 KM TO CH. 118+600 KM
CONTRACT NO |  | :RDA/MFAP/ICB/OFID-04(A)
BILL No.6 : BRIDGES,CULVERTS & RETAINING STRUCTURES
BOQ
Item |  | Description | Unit | Quantity | Rate | Amount (Rs.)
Bill | Pay
6.1 |  | CULVERTS
1 | 705(1) | Aggregate backfill | cu.m | 3456 | 5313.61 | 18363836.16
2 | 705(2) | Filter medium | cu.m | 1728 | 6199.21 | 10712234.88
3 | 705(3) | Impervious layer (Clay puddle) | cu.m | 311 | 3542.41 | 1101689.51
4 | 706(1) | Weep hole, PVC pipe (Type 600) - 75mm diameter | l.m | 600 | 2214 | 1328400
5 | 707(1) | Laying & joining of pipes-600 mm diameter | l.m | 150 | 13284.02 | 1992603
6 | 707(2) | Laying & joining of pipes-900 mm diameter | l.m | 150 | 17712.03 | 2656804.5
7 | 707(3) | Laying & joining of pipes-1200 mm diameter | l.m | 150 | 22582.84 | 3387426
8 | 1001(1a) | Concrete: Grade A 25(20) | cu.m | 1080 | 24354.04 | 26302363.2
9 | 1001(1b) | Concrete: Grade A 20(20) | cu.m | 100 | 23025.64 | 2302564
10 | 1001(2) | Concrete: Grade C 15(37.5) | cu.m | 900 | 20811.64 | 18730476
11 | 1002(1) | Tor steel reinforcement | ton. | 120 | 287820.53 | 34538463.6
12 | 1002(1) | Mild steel reinforcement | ton. | 20 | 265680.49 | 5313609.8
13 | 1008(1) | Formwork smooth finish | sq.m | 4800 | 1948.32 | 9351936
14 | 1008(2) | Formwork rough finish | sq.m | 3600 | 1948.32 | 7013952
15 | 1011(1) | 20 mm -400mm long Steel dowels | nr | 30 | 1771.2 | 53136
16 | 1303(3) | Painting of culverts and bridges with weather shield emulsion paint two coats | sq.m | 720 | 2214 | 1594080
17 | 1303(4) | Stencilling and numbering of culverts & parapets | nr | 60 | 2656.8 | 159408
18 | 1006(1a) | R R Masonry using cement mortar 1:5 | Cum | 100 | 13284.02 | 1328402
19 | 1006(1b) | R R Masonry with available rubble using cement mortar 1:5 | Cum | 300 | 6199.21 | 1859763
20 | 1006(3) | Plastering, 1:3 cement sand mix, 12.5mm thick | sq.m | 200 | 1771.2 | 354240
21 | 302(11) | Dewatering | LS | 1 | 2656804.9 | 2656804.9
Total Carried Forward | [5 empty] | 151102192.55
Total Brought Forward | [5 empty] | 151102192.55
6.2 |  | RETAINING STRUCTURES
1 | 705(1) | Aggregate backfill | cu.m | 1400 | 4428.01 | 6199214
2 | 705(2) | Filter medium | cu.m | 700 | 5313.61 | 3719527
3 | 705(3) | Impervious layer (Clay puddle) | cu.m | 700 | 3542.41 | 2479687
4 | 706(1) | Weep hole, PVC pipe (Type 600) - 75mm diameter | l.m | 467 | 2214 | 1033938
5 | 1001(1a) | Concrete: Grade A 25(20) | cu.m | 2300 | 23911.24 | 54995852
6 | 1001(2) | Concrete: Grade15(37.5) | cu.m | 380 | 20811.64 | 7908423.2
7 | 1002(1) | Tor steel reinforcement | ton. | 190 | 287820.53 | 54685900.7
8 | 1006(1a) | R R Masonry using cement mortar 1:5 | cu.m | 600 | 13284.02 | 7970412
9 | 1006(1b) | 300 x 150 rubble paving with 1:3:6(37.5) concrete mortar | cu.m | 100 | 15940.83 | 1594083
10 | 1006(3) | Plastering, 1:3 cement sand mix, 12.5mm thick | sq.m | 500 | 1771.2 | 885600
11 | 1008(1) | Formwork smooth finish | sq.m | 6545 | 1948.32 | 12751754.4
12 | 1008(2) | Formwork rough finish | sq.m | 5355 | 1948.32 | 10433253.6
13 | 1011(1) | 25 mm - 600mm long Steel dowels | nr | 200 | 2656.8 | 531360
GABION WALLS
14 | 1001(1a) | Concrete: Grade A 20(20) | cu.m | 135 | 23025.64 | 3108461.4
15 | 1001(2) | Concrete: Grade B 15(37.5) | cu.m | 30 | 20811.64 | 624349.2
16 | 1002(1) | Tor steel reinforcement | ton. | 5 | 287820.53 | 1439102.65
17 | 805(1) | Gabion | Cum | 900 | 17712.03 | 15940827
18 | 805(2) | Filter fabric | Sqm | 720 | 708.48 | 510105.6
19 | 302(11) | Dewatering | LS | 1 | 1771203.27 | 1771203.27
Total Carried Forward | [5 empty] | 339685246.57
Total Brought Forward | [5 empty] | 339685246.57
6.4 |  | RECONSTRUCTION/WIDENING OF BRIDGE No. 115/4
A. REMOVAL OF EXISTING STRUCTURES
1 | 202(7) | Removal and disposal of existing bridge deck, dismantling of steel work, transporting the reusalble material to a place within 10km. as directed and stacking the same after completion of the first stage and allowing traffic on the same and dimolishing the existing substructure to level specified in the drawing. | LS | 1 | 1771203.27 | 1771203.27
B. FOUNDATION & SUBSTRUCTURE
Abutment & Wingwall
Clearing & Grubbing
2 | 201(1) | Clearing & Grubbing | m2 | 100 | 442.8 | 44280
Excavation & Backfill
3 | 302(15) | Excavation in unclassified soil and backfill for abutments, and wingwalls. | m3 | 210 | 3099.61 | 650918.1
4 | 302(2) | Excavation in highly weathered rock | m3 | 25 | 3985.21 | 99630.25
5 | 302(4) | Excavation in hard rock | m3 | 20 | 7084.81 | 141696.2
6 | 302(9) | Preparation of base for foundation | L.S. | 1 | 442800.82 | 442800.82
7 | 302(10) | Construction of necessary cofferdams cribs sheeting, shoring and bracing and their subsequent removal. | L.S. | 1 | 1328402.45 | 1328402.45
8 | 302(11) | Dewatering | L.S. | 1 | 1771302.34 | 1771302.34
|  | Concrete For Structures |  |  |  | 0
9 | 1001(1a) | Class A concrete of Grade 30 (20) in bottom slab & drop wall. | m3 | 23.5 | 26568.05 | 624349.18
10 | 1001(1b) | Class A concrete of Grade 30 (20) in side walls, wing walls 7 corbel for approach slab | m3 | 24.5 | 26568.05 | 650917.23
11 | 1001(3a) | Class C concrete of nominal mix 1:3:6(20) as screed under bottom slab of box Bridge & wingwalls. | m3 | 7 | 21254.44 | 148781.08
12 | 1001(1c) | Class A concrete of Grade 25(20) in approach slabs. | m3 | 8 | 24354.04 | 194832.32
Total Carried Forward | [5 empty] | 347554359.81
Total Brought Forward | [5 empty] | 347554359.81
Formwork
13 | 1008(2) | Rough finish formwork for bottom slabs & drop wall of box bridge | m2 | 35 | 2214 | 77490
14 | 1008(1a) | Smooth finish formwork for side walls, wingwalls, corbbel for approach slab | m2 | 110 | 2214 | 243540
Reinforcement
15 | 1002(1a) | Cold worked deformed high yield steel bars of Grade 460 in bottom slabs & drop wall of box bridg | M.T. | 2.45 | 287820.53 | 705160.3
16 | 1002(1b) | Cold worked deformed high yield steel bars of Grade 460 in side walls, wingwalls, corbbel for approach slab. | M.T. | 3 | 287820.53 | 863461.59
17 | 1002(1c) | Hot rolled mild steel bars of Grade 250 in bearing pads and approach slabs. | M.T. | 0.25 | 287820.52 | 71955.13
Weep Holes
18 | 706(1) | Forming weep holes in abutments & wingwalls using 110mm dia. P.V.C. pipes and finished smooth with dripledge and surround complete as per drawing. | L.m. | 16 | 2656.8 | 42508.8
|  | Drainage Backfill Material |  |  |  | 0
19 | 705(1) | 50-200mm. dry stone lining behind abutment & wingwalls as per drawing. | m3 | 25 | 6199.21 | 154980.25
20 | 705(2) | 75mm. thick 40mm. stone filter layer behind dry stone lining as per drawing. | m3 | 4 | 5756.41 | 23025.64
21 | 705(3) | Clay puddled & laid behind abutments & wingwalls to form the impervious layer as per drawing. | m3 | 3 | 3985.21 | 11955.63
Total Carried Forward | [5 empty] | 349748437.15
Total Brought Forward | [5 empty] | 349748437.15
C. SUPER STRUCTURE
Concrete For Structures
1 | 1001(1a) | Class A Grade 30(20) concrete in top slab of box bridge | m3 | 18 | 26568.05 | 478224.9
2 | 1001(1c) | Class A concrete of Grade 25(20) in footwalks and footwalk ramps | m3 | 10 | 23911.24 | 239112.4
Form work
3 | 1008(1a) | Smooth finish formwork for top slab concrete of box bridge | m2 | 65 | 2214 | 143910
4 | 1008(1b) | Smooth finish formwork on sides for foot walk concreting | m2 | 26 | 2214 | 57564
Reinforcement
5 | 1002(1b) | Hot rolled mild steel bars of Grade 250 in top slab of box bridge | M.T. | 2.5 | 287820.53 | 719551.33
6 | 1002(1a) | Cold worked deformed high yield steel bars Grade 460 in foot walks. | M.T. | 0.1 | 287820.5 | 28782.05
Railings
7 | 1018(1) | Precast reinforced concrete railing & uprights in Class A Grade 25(20) concrete inclusive of light reinforcement & mould as per drawing No. T/B/102 A & B. | L.m. | 15 | 22140.04 | 332100.6
8 | 1019(1) | End pillasters in Class A concrete of Grade 25(20) with foundation type II as per drawing No. T/B/513 | Nos. | 4 | 177120.33 | 708481.32
|  | Guard Stones |  |  |  | 0
9 | 808(5) | Precast Concrete guard stones supplied and fixed as per Drawing. | Nos | 8 | 4428.01 | 35424.08
|  | Concrete Kerbs |  |  |  | 0
10 | 807(1) | Precast kerb in Class B Grade 25(20) concrete with light reinforcement & mould as per drawing No. T/B/512 | L.m. | 20 | 3099.61 | 61992.2
11 | 807(4) | Lower kerbs in Class B Grade 20(14) concrete cast insitu as per drawing. | L.m. | 10 | 3099.61 | 30996.1
Total Carried Forward | [5 empty] | 352584576.13
Total Brought Forward | [5 empty] | 352584576.13
Bridge Bearings
12 | 1010(2) | 75x12mm. hard rubber bearing pads supplied & laid over corbel for approach slab as per drawing. | L.m. | 18 | 3542.41 | 63763.38
Miscellaneous
13 | 1012(1) | 20mm Dia. 200mm long stainless steel dowels supplied fixed and grouted for the approach slab as per drawing. | Nos. | 20 | 6642.01 | 132840.2
14 | 1011(1a) | 20mm. Dia. 1800mm long hot rolled mild steel dowels driven into bed rock for abutment and wingwalls supplied fixed and grouted as per drawings | Nos. | 20 | 4428.01 | 88560.2
15 | 1014(1) | Bituminous sealing felt under approach slabs at capping beam ends to prevent bitumen running on capping beam as per drawing. | L.m. | 18 | 2656.8 | 47822.4
16 | 1016(1d) | Service duct of size 350x200mm. formed in deck as per drawing. | L.m. | 20 | 8856.02 | 177120.4
17 | 1017(1) | 500x450x75mm. thick paving slabs in Class B Grade 25(20) concrete inclusive of light reinforcement and smooth shuttering provided as per drawing. | Nos | 20 | 3099.61 | 61992.2
18 | 806(4) | 450x450x50mm. thick paving slabs in Class B Grade 25(20) concrete inclusive of light reinforcement and smooth shuttering provided as per drawing. | Sqm | 9 | 4428.01 | 39852.09
19 | 1020(1a) | 110mm. dia. P.V.C. rain water outlets supplied and fixed through deck as per drawing. | Nos. | 6 | 2214 | 13284
20 | 1020(1c) | 50mm. dia. P.V.C. drain pipes supplied and fixed through deck as per drawing. | Nos. | 6 | 1771.2 | 10627.2
Total Carried Forward | [5 empty] | 353220438.2
Total Brought Forward | [5 empty] | 353220438.2
6.5 |  | RECONSTRUCTION/WIDENING OF BRIDGE No. 116/5
A. REMOVAL OF EXISTING STRUCTURES
1 | 202(7) | Removal and disposal of existing bridge deck, dismantling of steel work, transporting the reusalble material to a place within 10km. as directed and stacking the same after completion of the first stage and allowing traffic on the same and dimolishing the existing substructure to level specified in the drawing. | LS | 1 | 2214004.08 | 2214004.08
B. FOUNDATION & SUBSTRUCTURE
Abutment & Wingwall
Clearing & Grubbing
2 | 201(1) | Clearing & Grubbing | m2 | 184 | 442.8 | 81475.2
Excavation & Backfill
3 | 302(15) | Excavation in unclassified soil and backfill for abutments, and wingwalls. | m3 | 1320 | 3099.61 | 4091485.2
4 | 302(2) | Excavation in highly weathered rock | m3 | 110 | 5313.61 | 584497.1
5 | 302(4) | Excavation in hard rock | m3 | 10 | 7084.81 | 70848.1
6 | 302(9) | Preparation of base for foundation | L.S. | 1 | 885601.63 | 885601.63
7 | 302(10) | Construction of necessary cofferdams cribs sheeting, shoring and bracing and their subsequent removal. | L.S. | 1 | 4428008.17 | 4428008.17 | 147600.27
8 | 302(11) | Dewatering | L.S. | 1 | 1771203.27 | 1771203.27
|  | Concrete For Structures |  |  |  | 0
9 | 1001(1a) | Class A concrete of Grade 30 (20) in foundation slab of abutment and wing wall. | m3 | 175 | 28339.25 | 4959368.75
10 | 1001(1b) | Class A concrete of Grade 30 (20) in abutment and wing walls | m3 | 190 | 26568.05 | 5047929.5
11 | 1001(3a) | Class C concrete of nominal mix 1:3:6(20) as screed under bottom slab of box Bridge & wingwalls. | m3 | 11 | 22140.04 | 243540.44
12 | 1001(1c) | Class A concrete of Grade 25(20) in approach slabs. | m3 | 13 | 24796.85 | 322359.05
13 | 1001(1d) | Class A concrete of Grade 30 (20) in capping beam, ballast wall, curtain walls and bearing pads | m3 | 20 | 26568.05 | 531361
Total Carried Forward | [5 empty] | 378452119.69
Total Brought Forward | [5 empty] | 378452119.69
Formwork
14 | 1008(2) | Rough finish formwork for foundation slabs of abutment and wing walls | m2 | 95 | 2656.8 | 252396
15 | 1008(1a) | Smooth finish formwork for abutment and wingwalls | m2 | 490 | 2656.8 | 1301832
16 | 1008(1b) | Smooth finish formwork for abutment capping beams, ballast walls, curtain walls, bearing pads and approach slabsand wingwalls | m2 | 89 | 2656.8 | 236455.2
Reinforcement
17 | 1002(1a) | Cold worked deformed high yield steel bars of Grade 460 in foundation slabs of abutment and wing walls | M.T. | 14 | 287820.53 | 4029487.42
18 | 1002(1b) | Cold worked deformed high yield steel bars of Grade 460 in abutments and wingwalls | M.T. | 16 | 287820.53 | 4605128.48
19 | 1002(1c) | Hot rolled mild steel bars of Grade 250 in bearing pads corbel and approach slabs. | M.T. | 0.2 | 287820.55 | 57564.11
20 | 1002(1d) | Cold worked deformed high yield steel bars of Grade 460 in abutment capping beams, curtain walls, ballast walls, bearing pads, corbel and approach slabs | M.T. | 2.75 | 287820.53 | 791506.46
|  | Weep Holes |  |  |  | 0
21 | 706(1) | Forming weep holes in abutments & wingwalls using 110mm dia. P.V.C. pipes and finished smooth with dripledge and surround complete as per drawing. | L.m. | 110 | 2214 | 243540
|  | Drainage Backfill Material |  |  |  | 0
22 | 705(1) | 50-200mm. dry stone lining behind abutment & wingwalls as per drawing. | m3 | 25 | 5313.61 | 132840.25
23 | 705(2) | 75mm. thick 40mm. stone filter layer behind dry stone lining as per drawing. | m3 | 4 | 6199.21 | 24796.84
24 | 705(3) | Clay puddled & laid behind abutments & wingwalls to form the impervious layer as per drawing. | m3 | 3 | 3542.41 | 10627.23
Total Carried Forward | [5 empty] | 390138293.68
Total Brought Forward | [5 empty] | 390138293.68
C. SUPER STRUCTURE
Concrete For Structures
1 | 1001(1a) | Infiller concrete of Class A Grade 40(20) between beams in bridge deck inclusive of end make up, screed and camber. | m3 | 90 | 30996.06 | 2789645.4
2 | 1001(1c) | Class A concrete of Grade 25(20) in footwalks and footwalk ramps | m3 | 27 | 24796.85 | 669514.95
Formwork
4 | 1008(1b) | Smooth finish formwork on sides for deck and foot walk concreting | m2 | 60 | 2656.8 | 159408
Reinforcement
5 | 1002(1b) | Hot rolled mild steel bars of Grade 250 intie rods of deck | M.T. | 0.4 | 287820.53 | 115128.21
6 | 1002(1a) | Cold worked deformed high yield steel bars Grade 460 in deck and foot walks. | M.T. | 3.5 | 287820.53 | 1007371.86
Prestressed Concrete
7 | 1003(1) | Pre-tensioned precast concrete beams of cast length 16.5 m supplied as per drawing No. T/B/501A | Nos. | 19 | 309960.57 | 5889250.83
8 | 1003(2) | 16.5m long Pre-tensioned precast concrete beams launched into position as per drawing. | Nos. | 19 | 132840.24 | 2523964.56
Railings
9 | 1018(1) | Precast reinforced concrete railing & uprights in Class A Grade 25(20) concrete inclusive of light reinforcement & mould as per drawing No. T/B/102 A & B. | L.m. | 35 | 22140.04 | 774901.4
10 | 1019(1) | End pillasters in Class A concrete of Grade 25(20) with foundation type II as per drawing No. T/B/513 | Nos. | 4 | 177120.33 | 708481.32
Concrete Kerbs
11 | 807(1) | Precast kerb in Class B Grade 25(20) concrete with light reinforcement & mould as per drawing No. T/B/512 | L.m. | 40 | 3099.61 | 123984.4
12 | 807(4) | Lower kerbs in Class B Grade 20(14) concrete cast insitu as per drawing. | L.m. | 20 | 2656.8 | 53136
Total Carried Forward | [5 empty] | 404953080.61
Total Brought Forward | [5 empty] | 404953080.61
Expansion joints
13 | 1009(1) | Supplying and fixing of mild steel angle iron & hard rubber expansion joint as per drawing No. T/B/107 Rev.1 | L.m. | 20 | 3542.41 | 70848.2
Bridge Bearings
14 | 1010(2) | 75x12mm. hard rubber bearing pads supplied & laid over capping beam and corbel for deck and approach slab as per drawing. | L.m. | 36 | 3542.41 | 127526.76
Miscellaneous
15 | 1012(1) | 20mm Dia. 200mm long stainless steel dowels supplied fixed and grouted at fixed ends as per drawing. | Nos. | 22 | 6642.01 | 146124.22
16 | 1011(1a) | 20mm. Dia.1800mm long hot rolled mild steel dowels driven into bed rock for abutment and wingwalls supplied fixed and grouted as per drawings | Nos. | 20 | 4428.01 | 88560.2
17 | 1011(1b) | 25mm Dia. 200mm long stainless steel dowels supplied fixed and grouted at fixed for approach slabs as per drawing | Nos. | 42 | 7084.81 | 297562.02
18 | 1014(1) | Bituminous sealing felt under approach slabs at capping beam ends to prevent bitumen running on capping beam as per drawing. | L.m. | 22 | 2656.8 | 58449.6
19 | 1016(1d) | Service duct of size 350x230mm. formed in deck as per drawing. | L.m. | 70 | 4428.01 | 309960.7
20 | 1017(1a) | 500x450x75mm. thick paving slabs in Class B Grade 25(20) concrete inclusive of light reinforcement and smooth shuttering provided as per drawing. | Nos. | 35 | 3099.61 | 108486.35
21 | 1017(1b) | 500x450x100m. thick paving slabs in Class B Grade 25(20) concrete inclusive of light reinforcement and smooth shuttering provided as per drawing. | Nos. | 35 | 3542.41 | 123984.35
22 | 806(4b) | 450x450x100mm. thick paving slabs in Class B Grade 25(20) concrete inclusive of light reinforcement and smooth shuttering provided as per drawing. | Sqm | 20 | 6642.01 | 132840.2
23 | 1020(1a) | 110mm. dia. P.V.C. rain water outlets supplied and fixed through deck as per drawing. | Nos. | 12 | 4428.01 | 53136.12
24 | 1020(1c) | 50mm. dia. P.V.C. drain pipes supplied and fixed through deck as per drawing. | Nos. | 6 | 3985.21 | 23911.26
Bill No. 6 Carried to Summary | [5 empty] | 406494470.59

## Bill 7
CONTRACT NAME |  | :MISCELLANEOUS FOREIGN AIDED PROJECT
REHABILITATION OF THE A-017 ROAD CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
FUNDED BY OPEC FUND FOR INTERNATIONAL DEVELOPMENT (OFID)
SECTION FROM CH. 112+600 KM TO CH. 118+600 KM
CONTRACT NO |  | :RDA/MFAP/ICB/OFID-04(A)
BILL No.7 : INCIDENTAL CONSTRUCTION
BOQ
Item |  | Description | Unit | Quantity | Rate | Amount (Rs.)
Bill | Pay
7.1 |  | PAVED SIDE WALKS AND PRECAST CONCRETE KERBS
1 | 806(a) | Supplying and paving of concrete paving blocks including preparation of Base layer and spreading and compaction of 50mm thick bed course material | sq.m | 900 | 3542.41 | 3188169
2 | 807(1) | Standard kerb | l.m | 540 | 2036.88 | 1099915.2
3 | 807(2) | Flat/Edge kerb | l.m | 50 | 2036.88 | 101844
4 | 807(3) | Drop kerb | l.m | 50 | 2036.88 | 101844
7.2 |  | GUARD RAILS AND GUARD STONES
1 | 808(5) | Guard stones | No | 150 | 6199.21 | 929881.5
2 | 808(1) | Guard rails (W - beam, galvanized steel) | l.m | 150 | 23911.24 | 3586686
3 | 809(3) a | Supply and fixing of Pedestrian hand rails as per Drawing (S Type) | m | 15 | 19483.24 | 292248.6
4 | 809(3) b | Supply and fixing of Pedestrian hand rails as per Drawing (P Type) | m | 15 | 19483.24 | 292248.6
7.3 |  | ROAD MARKINGS
1 | 810(1a) | Center line : Continuous | sq.m | 252 | 2656.8 | 669513.6
2 | 810(1b) | Center line : Intermittent | sq.m | 378 | 2656.8 | 1004270.4
3 | 810(1c) | Edge line : Continuous | sq.m | 1260 | 2656.8 | 3347568
4 | 810(1d) | Pedestrian crossing | sq.m | 150 | 2833.93 | 425089.5
5 | 810(3) | Reflecting road studs | nr | 126 | 2656.8 | 334756.8
7.4 |  | TRAFFIC SIGNS
1 | 811(1) | Single pole, sign area up to 0.5m2 | nr | 60 | 17712.03 | 1062721.8
2 | 811(2a) | Double pole, sign area up to 1.0m2 | nr | 3 | 221400.41 | 664201.23
3 | 811(2b) | Double pole, sign area up to 2.0m2 | nr | 2 | 265680.49 | 531360.98
4 | 811(3) | Chevron warning sign | nr | 120 | 17712.03 | 2125443.6
5 | 811(4) | Single pole, multiple sign area up to 1.0 m2 | nr | 3 | 154980.29 | 464940.87
7.5 |  | KERB INLETS
1 | 817(1) | Provide kerb inlets | nr | 30 | 3099.61 | 92988.3
Total Carried Forward | [5 empty] | 20315691.98
Total Brought Forward | [5 empty] | 20315691.98
7.6 |  | TRENCH EXCAVATION
1 | 815(1) | Trench excavation and reinstatements for utility installation | lm | 500 | 2656.8 | 1328400
7.7 |  | KILOMETRE POST AND BOUNDARY MARKERS |  |  |  | 0
1 | 819(1a) | Provide, install and paint new kilometre post | No. | 6 | 22140.04 | 132840.24
2 | 819(1b) | Provide, install and paint new Boundary marker | No. | 450 | 3321.01 | 1494454.5
7.8 |  | SOIL NAILING & HORIZONTAL DRAINS AND ROCK BOLTS |  |  |  | 0
1 | 820.1(2)a | Soil nails (more than 12m length) inserted into bore hole with grouting and coupling (32mm dia nail and125mm dia hole ). | Lm | 375 | 19926.04 | 7472265
2 | 820.1(2)b | Soil nails (less than or equal 12m length) inserted into bore hole with grouting and coupling (32mm dia nail and125mm dia hole ). | Lm | 250 | 19926.04 | 4981510
3 | 820.1(4)a | Coated Metallic Mesh for Grid Beam method including connecting clips and 16mm dia. 1m length hot dipped galvanized dowels, and other necessary accessories | Sqm | 100 | 12796.94 | 1279694
4 | 820.1(5) | Coir mesh | Sqm | 100 | 978.59 | 97859
5 | 820.1(6) | Concrete C30/20 boundary beams(250mm*250mm) including slope preparation, excavation, formwork, R/F and other necessary accessories | Lm | 75 | 13284.03 | 996302.25
6 | 820.1(7) | Concrete C30/20 grid beams (250mm*250mm) with nail heads including slope preparation, excavation, formwork, RF and other necessary accessories | Lm | 150 | 13284.02 | 1992603
7 | 820.1(8) | Shotcreting (wet mix -150mm thick) with concrete Grade 30 | Sqm | 100 | 35424.07 | 3542407
8 | 820.1(9) | Nail heads connecting beams 100mm*150mmwith nail heads in shotcrete face | Lm | 100 | 677.49 | 67749
9 | 820.1(10) | Pull-Out test for test nails and working nails | Nos | 4 | 210773.19 | 843092.76
10 | 820.2(2)a | Type 02 - Horizontal drains of perforated PVC pipe(75mm dia) with filter fabric | Lm | 50 | 9785.9 | 489295
Total Carried Forward | [5 empty] | 45034163.73
Total Brought Forward | [5 empty] | 45034163.73
11 | 820.2(2)b | Type 02 - Horizontal drains of perforated PVC pipe(90mm dia) with filter fabric | Lm | 50 | 11291.42 | 564571
12 | 802(1) | Planting/Seeding/Turfing on slope stabilized surface | Sqm | 100 | 4516.57 | 451657
13 | 803(1) | Plants from nursery, supplied planted , natured and maintained, during the establishment period | Nos | 200 | 13284.06 | 2656812
14 | 821(1) | Drilling for rock bolt in soil or soft rock | Lm | 18 | 15807.99 | 284543.82
15 | 821(2) | Drilling for rock bolt in rock | Lm | 72 | 26568.05 | 1912899.6
16 | 821(3) | Rock bolt | Lm | 95 | 19483.24 | 1850907.8
17 | 821(4) | Head Treatment with Cap | Nos | 3 | 8280.38 | 24841.14
18 | 821(5) | Head Treatment without Cap | Nos | 3 | 6774.85 | 20324.55
19 | 821(6) | Concrete Bearing Plates | Nos | 6 | 4428.01 | 26568.06
20 | 821(7) | Pull-out Tests for rock bolts | Nos | 2 | 255938.87 | 511877.74
324
Bill No. 7 Carried to Summary | [5 empty] | 53339166.44

## Bill 8.1
CONTRACT NAME |  | :MISCELLANEOUS FOREIGN AIDED PROJECT
REHABILITATION OF THE A-017 ROAD CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
FUNDED BY OPEC FUND FOR INTERNATIONAL DEVELOPMENT (OFID)
SECTION FROM CH. 112+600 KM TO CH. 118+600 KM
CONTRACT NO |  | :RDA/MFAP/ICB/OFID-04(A)
BILL No.8 : SCHEDULE OF DAY WORKS RATES
BOQ
Item |  | Description | Unit | Quantity | Rate | Amount (Rs.)
Bill | Pay
8.1 |  | LABOUR DAY WORKS
1 |  | Surveyor | hr | 60 | 885.61 | 53136.6
2 |  | Survey Assistant (skilled) | hr | 90 | 442.81 | 39852.9
3 |  | Laboratory Technician (skilled) | hr | 90 | 442.8 | 39852
4 |  | CAD Operator | hr | 90 | 398.52 | 35866.8
5 |  | Draughtsman | hr | 60 | 398.52 | 23911.2
6 |  | Foreman | hr | 60 | 398.52 | 23911.2
7 |  | Operator, Heavy equipment | hr | 120 | 398.52 | 47822.4
8 |  | Operator, Light equipment | hr | 120 | 398.52 | 47822.4
9 |  | Driver, Heavy duty vehicle | hr | 110 | 332.1 | 36531
10 |  | Driver, Light duty vehicle | hr | 110 | 265.68 | 29224.8
11 |  | Mechanic | hr | 45 | 398.52 | 17933.4
12 |  | Welder | hr | 45 | 398.52 | 17933.4
13 |  | Electrician | hr | 45 | 398.52 | 17933.4
14 |  | Carpenter | hr | 80 | 398.52 | 31881.6
15 |  | Mason | hr | 80 | 442.8 | 35424
16 |  | Steel Fixer | hr | 60 | 442.8 | 26568
17 |  | Semi-skilled workman | hr | 240 | 354.24 | 85017.6
18 |  | Unskilled workman (labour) | hr | 550 | 354.24 | 194832
Bill No. 8.1 Carried to Summary | [5 empty] | 805454.7

## Bill 8.2
CONTRACT NAME |  | :MISCELLANEOUS FOREIGN AIDED PROJECT
REHABILITATION OF THE A-017 ROAD CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
FUNDED BY OPEC FUND FOR INTERNATIONAL DEVELOPMENT (OFID)
SECTION FROM CH. 112+600 KM TO CH. 118+600 KM
CONTRACT NO |  | :RDA/MFAP/ICB/OFID-04(A)
BILL No.8 : SCHEDULE OF DAY WORKS RATES
BOQ
Item |  | Description | Unit | Quantity | Rate | Amount (Rs.)
Bill | Pay
8.2 |  | EQUIPMENT DAY WORKS
1 |  | Motor car, diesel, above 2,000 cc | km | 500 | 48.71 | 24355
2 |  | Double cabin Pickup 4WD, diesel, above 2,000 cc | km | 500 | 66.42 | 33210
3 |  | Lorry, 3 to 5 tones | hr | 20 | 885.58 | 17711.6
4 |  | Lorry, 5 to 10 tones | hr | 20 | 1107 | 22140
5 |  | Low-loader, 20 to 40 tones | hr | 6 | 8856.02 | 53136.12
6 |  | Site dumper, over 1.0 m3 | hr | 6 | 1328.4 | 7970.4
7 |  | Tipper truck, up to 5 tones | hr | 6 | 885.6 | 5313.6
8 |  | Tipper truck, 5 to 10 tones | hr | 6 | 1106.99 | 6641.94
9 |  | Tipper truck, 10 to 15 tones | hr | 8 | 1594.07 | 12752.56
10 |  | Bowser, water, up to 6,000 liters with Spray Bar | hr | 10 | 1549.79 | 15497.9
11 |  | Bowser, water, 6,000 to 10,000 liters with Spray Bar | hr | 10 | 1948.32 | 19483.2
12 |  | Bowser, diesel, up to 6,000 liters | hr | 6 | 2214 | 13284
13 |  | Bowser, diesel, 6,000 to 10,000 liters | hr | 3 | 3099.61 | 9298.83
14 |  | Bowser, bitumen, up to 10,000 liters | hr | 6 | 3099.61 | 18597.66
15 |  | Bowser, bitumen, over 10,000 liters | hr | 3 | 4428.01 | 13284.03
16 |  | Bitumen distributor, up to 4,500 liters | hr | 6 | 3099.61 | 18597.66
17 |  | Bitumen distributor, over 4,500 liters | hr | 6 | 4428.01 | 26568.06
18 |  | Bitumen hand sprayer | hr | 6 | 885.6 | 5313.6
19 |  | Farm Tractor & Broom over 2m width | hr | 6 | 708.48 | 4250.88
20 |  | Farm tractor, with trailer minimum 3 tone | hr | 8 | 442.8 | 3542.4
21 |  | Bulldozer, wheeled or Tracked up to 100 HP | hr | 3 | 4428.01 | 13284.03
22 |  | Bulldozer, wheeled or Tracked 100 to 200 HP | hr | 6 | 6642.01 | 39852.06
23 |  | Bulldozer, wheeled or Tracked 200 to 300 HP | hr | 6 | 7527.61 | 45165.66
24 |  | Backhoe, wheeled, 50 - 100 HP | hr | 8 | 1771.2 | 14169.6
25 |  | Backhoe, wheeled, 100 - 200 HP | hr | 15 | 1948.32 | 29224.8
26 |  | Backhoe, tracked, 50 - 100 HP | hr | 6 | 2656.8 | 15940.8
27 |  | Backhoe, tracked, 100 - 200 HP | hr | 6 | 3542.41 | 21254.46
Total Carried Forward | [5 empty] | 509840.85
Total Brought Forward | [5 empty] | 509840.85
28 |  | Front-end Loader, Tracked or wheeled, 50 to 100 HP | hr | 6 | 1771.2 | 10627.2
29 |  | Front-end Loader, wheeled, 100 to 200 HP | hr | 3 | 2214 | 6642
30 |  | Motor grader, up to 100 HP | hr | 3 | 3365.29 | 10095.87
31 |  | Motor grader, 100 to 150 HP | hr | 6 | 3542.41 | 21254.46
32 |  | Steel-wheeled roller, static, 8 to 12 tones | hr | 6 | 3985.21 | 23911.26
33 |  | Steel-wheeled roller, vibratory, 4 to 8 tones | hr | 6 | 3985.21 | 23911.26
34 |  | Steel-wheeled roller, vibratory, 10 tones | hr | 6 | 4428.01 | 26568.06
35 |  | Pneumatic-tired roller, 8 to 12 tones | hr | 3 | 4428.01 | 13284.03
36 |  | Tandem roller, 6 to 8 tones, Vibrating | hr | 6 | 4428.01 | 26568.06
37 |  | Hand roller, vibratory, 1/2 - 1 tone | hr | 6 | 885.6 | 5313.6
38 |  | Plate compactor, vibratory, over 90 kg | hr | 6 | 708.48 | 4250.88
39 |  | Rammer, mechanical, over 60 kg | hr | 6 | 708.48 | 4250.88
40 |  | Mobile Crane over 15 tones | hr | 3 | 13284.02 | 39852.06
41 |  | Asphalt mixing plant, over 60 tones/hr | hr | 3 | 57564.11 | 172692.33
42 |  | Crushing and screening plant, over 80 tones/hr | hr | 3 | 53136.1 | 159408.3
43 |  | Asphalt paver, wheeled or Tracked 60 tones/hr | hr | 3 | 17712.03 | 53136.09
44 |  | Asphalt paver, wheeled or Tracked over 80 tones/hr | hr | 3 | 22140.04 | 66420.12
45 |  | Chip spreader, self-propelled | hr | 3 | 8856.02 | 26568.06
46 |  | Drilling rig, crawler, over 75 mm diameter bit | hr | 3 | 22140.04 | 66420.12
47 |  | Rock drill, hand-held | hr | 3 | 4428.01 | 13284.03
48 |  | Air compressor with hoses and tools, 250 to 600 cfm | hr | 3 | 3542.41 | 10627.23
49 |  | Water pump with hoses, 50 to 100 mm outlet | hr | 3 | 1771.2 | 5313.6
50 |  | Concrete mixer, 0.25 to 0.50 cu.m. | hr | 9 | 2214 | 19926
51 |  | Concrete mixer, over 0.50 cu.m. | hr | 6 | 3542.41 | 21254.46
52 |  | Generator, 10 to 50 KVA | hr | 3 | 6642.01 | 19926.03
53 |  | Welding set, electric, 300 - 400 amp | hr | 3 | 1771.2 | 5313.6
54 |  | Poker Vibrator, petrol driven | hr | 6 | 354.24 | 2125.44
Bill No. 8.2 Carried to Summary | [5 empty] | 1368785.88

## Bill 8.3
CONTRACT NAME |  | :MISCELLANEOUS FOREIGN AIDED PROJECT
REHABILITATION OF THE A-017 ROAD CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
FUNDED BY OPEC FUND FOR INTERNATIONAL DEVELOPMENT (OFID)
SECTION FROM CH. 112+600 KM TO CH. 118+600 KM
CONTRACT NO |  | :RDA/MFAP/ICB/OFID-04(A)
BILL No.8 : SCHEDULE OF DAY WORKS RATES
BOQ
Item |  | Description | Unit | Quantity | Rate | Amount (Rs.)
Bill | Pay
8.3 |  | MATERIAL DAY WORKS
1 |  | Aggregate base, dense graded (37.5 mm) | cu.m | 12 | 2036.88 | 24442.56
2 |  | Aggregate, 6 mm (crusher fines) | cu.m | 12 | 1948.32 | 23379.84
3 |  | Aggregate, 12 mm | cu.m | 12 | 1948.32 | 23379.84
4 |  | Aggregate, 20 mm | cu.m | 12 | 1948.32 | 23379.84
5 |  | Aggregate, 25 mm | cu.m | 12 | 1948.32 | 23379.84
6 |  | Aggregate, 37.5 mm | cu.m | 12 | 1859.76 | 22317.12
7 |  | Asphalt concrete, cold mix | mt | 15 | 10627.22 | 159408.3
8 |  | Asphalt concrete, hot mix | mt | 15 | 10627.22 | 159408.3
9 |  | Bitumen emulsions, ( CRS 1, CRS 2, CSS 1) | ltr | 40 | 97.42 | 3896.8
10 |  | Bitumen prime coat, cutback MC 30 | ltr | 40 | 132.84 | 5313.6
11 |  | Bitumen, straight run, 60/70 penetration | ltr | 40 | 97.42 | 3896.8
12 |  | Bitumen, straight run, 80/100 penetration | ltr | 40 | 97.42 | 3896.8
13 |  | Block, cement, 400 x 200 x 100 mm | nr | 30 | 39.85 | 1195.5
14 |  | Brick, hand-cut | nr | 120 | 26.57 | 3188.4
15 |  | Cement, ordinary Portland | mt | 3 | 15055.23 | 45165.69
16 |  | Concrete pipe, reinforced 600 mm diameter - NP2 | l.m | 6 | 11070.02 | 66420.12
17 |  | Concrete pipe, reinforced 900 mm diameter - NP2 | l.m | 6 | 13284.02 | 79704.12
18 |  | Concrete pipe, reinforced 1,200 mm diameter - NP2 | l.m | 6 | 17712.03 | 106272.18
19 |  | Concrete, Grade 15/20 | cu.m | 1.5 | 13948.23 | 20922.35
20 |  | Concrete, Grade 20/20 | cu.m | 3 | 15498.03 | 46494.09
21 |  | Concrete, Grade 25/20 | cu.m | 3 | 16383.63 | 49150.89
22 |  | Concrete, Grade 30/20 | cu.m | 1.5 | 17269.23 | 25903.85
23 |  | Concrete, Grade 40/20 | cu.m | 0.75 | 22140.04 | 16605.03
24 |  | Formwork, steel | sq.m | 20 | 3542.41 | 70848.2
25 |  | Formwork, timber (smooth) | sq.m | 40 | 1771.2 | 70848
26 |  | Paint, emulsion | ltr | 8 | 1062.72 | 8501.76
27 |  | Paint, enamel | ltr | 3 | 1239.84 | 3719.52
Total Carried Forward | [5 empty] | 1091039.34
Total Brought Forward | [5 empty] | 1091039.34
28 |  | Pipe, PVC, 160 mm diameter (Type 600) | l.m | 15 | 1328.4 | 19926
29 |  | Lime | kg | 3 | 88.55 | 265.65
30 |  | Reinforcement, high-yield steel, Grade 460/425 | kg | 250 | 177.12 | 44280
31 |  | Reinforcement, mild steel, Grade 250 | kg | 200 | 177.12 | 35424
32 |  | Rubble, 100 - 150 mm | cu.m | 8 | 1771.2 | 14169.6
33 |  | Rubble, 150 - 225 mm | cu.m | 20 | 1771.2 | 35424
34 |  | River Sand | cu.m | 10 | 13284.02 | 132840.2
35 |  | Reflective, thermoplastic road paint | kg | 10 | 141.71 | 1417.1
36 |  | Timber, Class 2, Sri Lanka Timber Corporation | cu.m | 0.75 | 17712.03 | 13284.02
37 |  | Auto diesel | ltr | 150 | 127.53 | 19129.5
38 |  | Petrol | ltr | 80 | 162.94 | 13035.2
39 |  | kerosene Oil | ltr | 80 | 97.42 | 7793.6
Materials Sub Total | [5 empty] | 1428028.21
Percentage mark up applicable to materials in Bill No. 8.3 |  |  |  | 25% |  | 357007.05
Bill No. 8.3 Carried to Summary | [5 empty] | 1785035.26

## Bill 9
CONTRACT NAME |  | :MISCELLANEOUS FOREIGN AIDED PROJECT
REHABILITATION OF THE A-017 ROAD CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
FUNDED BY OPEC FUND FOR INTERNATIONAL DEVELOPMENT (OFID)
SECTION FROM CH. 112+600 KM TO CH. 118+600 KM
CONTRACT NO |  | :RDA/MFAP/ICB/OFID-04(A)
BILL No.9 : PROVISIONAL SUMS
BOQ
Item |  | Description | Unit | Quantity | Rate | Amount (Rs.)
Bill | Pay
9.1 |  | HIV AIDS PREVENTION
1 | 111(1) | Preparation and Implementation of HIV-AIDS Prevention Program | PS | Item | Allow | 100000
9.2 |  | SERVICES
1 | 112(1) | Demolition / Rebuilding of Property | PS | Item | Allow | 1000000
9.3 |  | MONITORING, CONTROLLING ENVIRONMENT HAZARDOUS ACTIVITIES AND TAKING REMEDIAL MEASURE
1 | 120(2) | Construction of Fish Pass, Velocity Breakers, Rain Water Infiltration Holes and Canopy Bridges as given in the Environmental Management and Monitoring Plan | PS | Item | Allow | 3000000
9.4 |  | REMOVAL AND REBUILDING EXISTING STRUCTURES
1 | 202(6a) | Allow for demolishing of culverts, dressed stone structures, fences etc. and removal of obstructions and objectionable materials in preparing right of way and rebuilding of parapet walls, fence, gates or any part of permanent building to the prevailed condition. | PS | Item | Allow | 6000000
9.5 |  | UTILITIES RELOCATION
1 | 203(1) | Diversion, Protection or Removal of Electrical services | PS | Item | Allow | 13000000
2 | 203(2) | Diversion, Protection or Removal of Water services | PS | Item | Allow | 5000000
3 | 203(3) | Diversion, Protection or Removal of Telecommunication services | PS | Item | Allow | 5000000
9.6 |  | SOIL NAILING AND HORIZONTAL DRAINS AND ROCK BOLTS
1 | 820.1(1) | Temporary working platform for soil nailing and rock bolts works | PS | Item | Allow | 1000000
9.7 |  | MANHOLES, CATCHPITS AND INLETS
1 | 703(5) | Grade adjustment of existing manholes | PS | Item | Allow | 300000
9.8 |  | HOUSING FOR THE EMPLOYER
1 | 124(3) | Provide Housing, Type 3 | PS | Item | Allow | 1600000
Bill No. 8.1 Carried to Summary | [5 empty] | 36000000

## PF
CONTRACT NAME
:MISCELLANEOUS FOREIGN AIDED PROJECT
REHABILITATION OF THE A-017 ROAD CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
FUNDED BY OPEC FUND FOR INTERNATIONAL DEVELOPMENT (OFID)
SECTION FROM CH. 112+600 KM TO CH. 118+600 KM
CONTRACT NO
| :RDA/MFAP/ICB/OFID-04(A) | [5 empty] | Interim Valuation No. | #REF!
[7 empty] | Period Ending | #REF!
PRICE FLUCTUATION.
F = 0.966 ( V - Vna ) * E all inputs Px ( Ixc - Ixb )
100 Ixb
All inputs Where:
F = Price adjustment for the period concerned
V = Current Valuation of workdone for the Period.
V na = Value of non Adjustable element. Or value of work not considered for price variation.
Px = Input percentage of input named X
l xc = Currenet indices of input X
lxb = Base indices of input X
A | Amount Subject to Price Adjustment for the Month of December 2022
| No | Description |  |  |  | Amount (SLR) | Amount (SLR)
| 1 | Work Done Bill 1 - 9 + Variation Claims |  |  |  | #REF!
[7 empty] | #REF! |  | 535616797.19
Less
| 1 | Bill 1 - Preliminary & General. |  |  |  | #REF!
| 2 | Provisional Sums (Non Adjustable). |  |  |  | #REF!
| 3 | Extra Work & Variation on the Prices Prevailing |  |  |  | #REF!
| 4 | Day Works |  |  |  | #REF!
| 5 | Claims |  |  |  | #REF!
|  | Total Non Adjustable |  |  |  |  | #REF! |  | 484767643.95
| Amount Subject to Price Adjustment for the Month of December 2022 | [5 empty] | #REF! |  | 50849153.24
Prepared By | [7 empty] | Submitted by
J Garusinghe | [7 empty] | WA Premarathna
Quantity Surveyor | [7 empty] | Project Manager
B | Price Adjustment Factor Sub clause( 13.8 PCC & Ap.to.Ten.)
| Ref | Input |  | Input % Px |  | Indices |  | Sum of All Inputs Px(Ixc-Ixb)/Ixb | 2022.8
[6 empty] | Base Index (Aug 2021) Ixb | Current Index (Dec 2022) Ixc
2343.1
| M1 | Cement |  | 2.43 |  | 696.6 | 1742.4 | 3.6481
| M6 | Rubble |  | 0.44 |  | 885.9 | 2343.1 | 0.72375 | 1036.4
| M7 | Metal |  | 1.67 |  | 429.9 | 1036.4 | 2.356
| M8 | Sand |  | 1.09 |  | 3929.8 | 6300.2 | 0.65747 | 6672.7
| M13 | Steel Reinforcement |  | 10.41 |  | 1089 | 2092 | 9.5879
| M21 | Timber |  | 1.11 |  | 1225 | 1808.5 | 0.52872 | 2215.5
| M30C | Bitumen 60/70 |  | 1.32 |  | 494.9 | 1104.9 | 1.627
| M45 | Earth |  | 0.77 |  | 1400 | 2481.3 | 0.59471 | 1808.5
| M48 | ABC |  | 1.3 |  | 253.4 | 591 | 1.732
| P1 | Small Equipment |  | 20.07 |  | 475.9 | 588.7 | 4.7571 | 1104.9
| P2 | Heavy Equipment |  | 22.93 |  | 418.2 | 517.3 | 5.4337
| P3 | Fuel |  | 11.98 |  | 1084.7 | 4120 | 33.5235 | 2481.3
| L1 | Skilled Labour |  | 3.31 |  | 588.3 | 750.6 | 0.91316
| L2 | S/SK Labour |  | 5.56 |  | 638.4 | 814.5 | 1.5337 | 591
| L3 | U/SK Labour |  | 5.61 |  | 725.3 | 925.4 | 1.5477
|  | Sub Total |  | 90 |  |  |  |  | 588.7
| Price Adjustment Factor | [6 empty] | 69.1645
517.3
C | Price Adjustment Amount in SLR Currency
4138.4
| F = | 0.966 ( V - Vna ) * E all inputs Px ( Ixc - Ixb )
|  | 100 Ixb | [6 empty] | 750.6
| = | 0.966 * | #REF! | *( | 69.1645 | )
|  |  | 100 | [5 empty] | 814.5
| = | #REF!
925.4
D | Adjustments To Date
| Valuation |  | Value (Rs.)
| No. | Period | Total [A] | Non-Adjustable [B] |  | Adjustable [C=A-B] | Factor [D] | Amount (Rs.) [F]
| 03 | 01-12-2022 to 31-12-2022 | #REF! | #REF! |  | #REF! | 69.1645 | #REF!
| Adjustments To Date | [6 empty] | #REF! | #REF!
Prepared By | [7 empty] | Submitted by
J Garusinghe | [7 empty] | WA Premarathna
Quantity Surveyor | [7 empty] | Project Manager

## Bill 6 (2)
CONTRACT NAME |  | :MISCELLANEOUS FOREIGN AIDED PROJECT
REHABILITATION OF THE A-017 ROAD CORRIDOR PROJECT (SURIYAKANDA - RAKWANA)
FUNDED BY OPEC FUND FOR INTERNATIONAL DEVELOPMENT (OFID)
SECTION FROM CH. 112+600 KM TO CH. 118+600 KM
CONTRACT NO |  | :RDA/MFAP/ICB/OFID-04(A)
BILL No.6 : BRIDGES,CULVERTS & RETAINING STRUCTURES
BOQ
Item |  | Description | Unit | Quantity | Rate | Amount (Rs.)
Bill | Pay
6.1 |  | CULVERTS
1 | 705(1) | Aggregate backfill | cu.m | 3456 | 5313.61 | 18363836.16
2 | 705(2) | Filter medium | cu.m | 1728 | 6199.21 | 10712234.88
3 | 705(3) | Impervious layer (Clay puddle) | cu.m | 311 | 3542.41 | 1101689.51
4 | 706(1) | Weep hole, PVC pipe (Type 600) - 75mm diameter | l.m | 600 | 2214 | 1328400
5 | 707(1) | Laying & joining of pipes-600 mm diameter | l.m | 150 | 13284.02 | 1992603
6 | 707(2) | Laying & joining of pipes-900 mm diameter | l.m | 150 | 17712.03 | 2656804.5
7 | 707(3) | Laying & joining of pipes-1200 mm diameter | l.m | 150 | 22582.84 | 3387426
8 | 1001(1a) | Concrete: Grade A 25(20) | cu.m | 1080 | 24354.04 | 26302363.2
9 | 1001(1b) | Concrete: Grade A 20(20) | cu.m | 100 | 23025.64 | 2302564
10 | 1001(2) | Concrete: Grade C 15(37.5) | cu.m | 900 | 20811.64 | 18730476
11 | 1002(1) | Tor steel reinforcement | ton. | 120 | 287820.53 | 34538463.6
12 | 1002(1) | Mild steel reinforcement | ton. | 20 | 265680.49 | 5313609.8
13 | 1008(1) | Formwork smooth finish | sq.m | 4800 | 1948.32 | 9351936
14 | 1008(2) | Formwork rough finish | sq.m | 3600 | 1948.32 | 7013952
15 | 1011(1) | 20 mm -400mm long Steel dowels | nr | 30 | 1771.2 | 53136
16 | 1303(3) | Painting of culverts and bridges with weather shield emulsion paint two coats | sq.m | 720 | 2214 | 1594080
17 | 1303(4) | Stencilling and numbering of culverts & parapets | nr | 60 | 2656.8 | 159408
18 | 1006(1a) | R R Masonry using cement mortar 1:5 | Cum | 100 | 13284.02 | 1328402
19 | 1006(1b) | R R Masonry with available rubble using cement mortar 1:5 | Cum | 300 | 6199.21 | 1859763
20 | 1006(3) | Plastering, 1:3 cement sand mix, 12.5mm thick | sq.m | 200 | 1771.2 | 354240
21 | 302(11) | Dewatering | LS | 1 | 2656804.9 | 2656804.9
Total Carried Forward | [5 empty] | 151102192.55
Total Brought Forward | [5 empty] | 151102192.55
6.2 |  | RETAINING STRUCTURES
1 | 705(1) | Aggregate backfill | cu.m | 1400 | 4428.01 | 6199214
2 | 705(2) | Filter medium | cu.m | 700 | 5313.61 | 3719527
3 | 705(3) | Impervious layer (Clay puddle) | cu.m | 700 | 3542.41 | 2479687
4 | 706(1) | Weep hole, PVC pipe (Type 600) - 75mm diameter | l.m | 467 | 2214 | 1033938
5 | 1001(1a) | Concrete: Grade A 25(20) | cu.m | 2300 | 23911.24 | 54995852
6 | 1001(2) | Concrete: Grade15(37.5) | cu.m | 380 | 20811.64 | 7908423.2
7 | 1002(1) | Tor steel reinforcement | ton. | 190 | 287820.53 | 54685900.7
8 | 1006(1a) | R R Masonry using cement mortar 1:5 | cu.m | 600 | 13284.02 | 7970412
9 | 1006(1b) | 300 x 150 rubble paving with 1:3:6(37.5) concrete mortar | cu.m | 100 | 15940.83 | 1594083
10 | 1006(3) | Plastering, 1:3 cement sand mix, 12.5mm thick | sq.m | 500 | 1771.2 | 885600
11 | 1008(1) | Formwork smooth finish | sq.m | 6545 | 1948.32 | 12751754.4
12 | 1008(2) | Formwork rough finish | sq.m | 5355 | 1948.32 | 10433253.6
13 | 1011(1) | 25 mm - 600mm long Steel dowels | nr | 200 | 2656.8 | 531360
GABION WALLS
14 | 1001(1a) | Concrete: Grade A 20(20) | cu.m | 135 | 23025.64 | 3108461.4
15 | 1001(2) | Concrete: Grade B 15(37.5) | cu.m | 30 | 20811.64 | 624349.2
16 | 1002(1) | Tor steel reinforcement | ton. | 5 | 287820.53 | 1439102.65
17 | 805(1) | Gabion | Cum | 900 | 17712.03 | 15940827
18 | 805(2) | Filter fabric | Sqm | 720 | 708.48 | 510105.6
19 | 302(11) | Dewatering | LS | 1 | 1771203.27 | 1771203.27
Total Carried Forward | [5 empty] | 339685246.57
Total Brought Forward
6.4 |  | RECONSTRUCTION/WIDENING OF BRIDGE No. 115/4
A. REMOVAL OF EXISTING STRUCTURES
1 | 202(7) | Removal and disposal of existing bridge deck, dismantling of steel work, transporting the reusalble material to a place within 10km. as directed and stacking the same after completion of the first stage and allowing traffic on the same and dimolishing the existing substructure to level specified in the drawing. | LS | 1 | 1771203.27 | 1771203.27
B. FOUNDATION & SUBSTRUCTURE
Abutment & Wingwall
Clearing & Grubbing
2 | 201(1) | Clearing & Grubbing | m2 | 100 | 442.8 | 44280
Excavation & Backfill
3 | 302(15) | Excavation in unclassified soil and backfill for abutments, and wingwalls. | m3 | 210 | 3099.61 | 650918.1
4 | 302(2) | Excavation in highly weathered rock | m3 | 25 | 3985.21 | 99630.25
5 | 302(4) | Excavation in hard rock | m3 | 20 | 7084.81 | 141696.2
6 | 302(9) | Preparation of base for foundation | L.S. | 1 | 442800.82 | 442800.82
7 | 302(10) | Construction of necessary cofferdams cribs sheeting, shoring and bracing and their subsequent removal. | L.S. | 1 | 1328402.45 | 1328402.45
8 | 302(11) | Dewatering | L.S. | 1 | 1771302.34 | 1771302.34
|  | Concrete For Structures |  |  |  | 0
9 | 1001(1a) | Class A concrete of Grade 30 (20) in bottom slab & drop wall. | m3 | 23.5 | 26568.05 | 624349.18
10 | 1001(1b) | Class A concrete of Grade 30 (20) in side walls, wing walls 7 corbel for approach slab | m3 | 24.5 | 26568.05 | 650917.23
11 | 1001(3a) | Class C concrete of nominal mix 1:3:6(20) as screed under bottom slab of box Bridge & wingwalls. | m3 | 7 | 21254.44 | 148781.08
12 | 1001(1c) | Class A concrete of Grade 25(20) in approach slabs. | m3 | 8 | 24354.04 | 194832.32
Total Carried Forward | [5 empty] | 7869113.24
Total Brought Forward | [5 empty] | 7869113.24
Formwork
13 | 1008(2) | Rough finish formwork for bottom slabs & drop wall of box bridge | m2 | 35 | 2214 | 77490
14 | 1008(1a) | Smooth finish formwork for side walls, wingwalls, corbbel for approach slab | m2 | 110 | 2214 | 243540
Reinforcement
15 | 1002(1a) | Cold worked deformed high yield steel bars of Grade 460 in bottom slabs & drop wall of box bridg | M.T. | 2.45 | 287820.53 | 705160.3
16 | 1002(1b) | Cold worked deformed high yield steel bars of Grade 460 in side walls, wingwalls, corbbel for approach slab. | M.T. | 3 | 287820.53 | 863461.59
17 | 1002(1c) | Hot rolled mild steel bars of Grade 250 in bearing pads and approach slabs. | M.T. | 0.25 | 287820.52 | 71955.13
Weep Holes
18 | 706(1) | Forming weep holes in abutments & wingwalls using 110mm dia. P.V.C. pipes and finished smooth with dripledge and surround complete as per drawing. | L.m. | 16 | 2656.8 | 42508.8
|  | Drainage Backfill Material |  |  |  | 0
19 | 705(1) | 50-200mm. dry stone lining behind abutment & wingwalls as per drawing. | m3 | 25 | 6199.21 | 154980.25
20 | 705(2) | 75mm. thick 40mm. stone filter layer behind dry stone lining as per drawing. | m3 | 4 | 5756.41 | 23025.64
21 | 705(3) | Clay puddled & laid behind abutments & wingwalls to form the impervious layer as per drawing. | m3 | 3 | 3985.21 | 11955.63
Total Carried Forward | [5 empty] | 10063190.58
Total Brought Forward | [5 empty] | 10063190.58
C. SUPER STRUCTURE
Concrete For Structures
1 | 1001(1a) | Class A Grade 30(20) concrete in top slab of box bridge | m3 | 18 | 26568.05 | 478224.9
2 | 1001(1c) | Class A concrete of Grade 25(20) in footwalks and footwalk ramps | m3 | 10 | 23911.24 | 239112.4
Form work
3 | 1008(1a) | Smooth finish formwork for top slab concrete of box bridge | m2 | 65 | 2214 | 143910
4 | 1008(1b) | Smooth finish formwork on sides for foot walk concreting | m2 | 26 | 2214 | 57564
Reinforcement
5 | 1002(1b) | Hot rolled mild steel bars of Grade 250 in top slab of box bridge | M.T. | 2.5 | 287820.53 | 719551.33
6 | 1002(1a) | Cold worked deformed high yield steel bars Grade 460 in foot walks. | M.T. | 0.1 | 287820.5 | 28782.05
Railings
7 | 1018(1) | Precast reinforced concrete railing & uprights in Class A Grade 25(20) concrete inclusive of light reinforcement & mould as per drawing No. T/B/102 A & B. | L.m. | 15 | 22140.04 | 332100.6
8 | 1019(1) | End pillasters in Class A concrete of Grade 25(20) with foundation type II as per drawing No. T/B/513 | Nos. | 4 | 177120.33 | 708481.32
|  | Guard Stones |  |  |  | 0
9 | 808(5) | Precast Concrete guard stones supplied and fixed as per Drawing. | Nos | 8 | 4428.01 | 35424.08
|  | Concrete Kerbs |  |  |  | 0
10 | 807(1) | Precast kerb in Class B Grade 25(20) concrete with light reinforcement & mould as per drawing No. T/B/512 | L.m. | 20 | 3099.61 | 61992.2
11 | 807(4) | Lower kerbs in Class B Grade 20(14) concrete cast insitu as per drawing. | L.m. | 10 | 3099.61 | 30996.1
Total Carried Forward | [5 empty] | 12899329.56
Total Brought Forward | [5 empty] | 12899329.56
Bridge Bearings
12 | 1010(2) | 75x12mm. hard rubber bearing pads supplied & laid over corbel for approach slab as per drawing. | L.m. | 18 | 3542.41 | 63763.38
Miscellaneous
13 | 1012(1) | 20mm Dia. 200mm long stainless steel dowels supplied fixed and grouted for the approach slab as per drawing. | Nos. | 20 | 6642.01 | 132840.2
14 | 1011(1a) | 20mm. Dia. 1800mm long hot rolled mild steel dowels driven into bed rock for abutment and wingwalls supplied fixed and grouted as per drawings | Nos. | 20 | 4428.01 | 88560.2
15 | 1014(1) | Bituminous sealing felt under approach slabs at capping beam ends to prevent bitumen running on capping beam as per drawing. | L.m. | 18 | 2656.8 | 47822.4
16 | 1016(1d) | Service duct of size 350x200mm. formed in deck as per drawing. | L.m. | 20 | 8856.02 | 177120.4
17 | 1017(1) | 500x450x75mm. thick paving slabs in Class B Grade 25(20) concrete inclusive of light reinforcement and smooth shuttering provided as per drawing. | Nos | 20 | 3099.61 | 61992.2
18 | 806(4) | 450x450x50mm. thick paving slabs in Class B Grade 25(20) concrete inclusive of light reinforcement and smooth shuttering provided as per drawing. | Sqm | 9 | 4428.01 | 39852.09
19 | 1020(1a) | 110mm. dia. P.V.C. rain water outlets supplied and fixed through deck as per drawing. | Nos. | 6 | 2214 | 13284
20 | 1020(1c) | 50mm. dia. P.V.C. drain pipes supplied and fixed through deck as per drawing. | Nos. | 6 | 1771.2 | 10627.2
Total Carried Forward | [5 empty] | 13535191.63
Total Brought Forward | [5 empty] | 13535191.63
6.5 |  | RECONSTRUCTION/WIDENING OF BRIDGE No. 116/5
A. REMOVAL OF EXISTING STRUCTURES
1 | 202(7) | Removal and disposal of existing bridge deck, dismantling of steel work, transporting the reusalble material to a place within 10km. as directed and stacking the same after completion of the first stage and allowing traffic on the same and dimolishing the existing substructure to level specified in the drawing. | LS | 1 | 2214004.08 | 2214004.08
B. FOUNDATION & SUBSTRUCTURE
Abutment & Wingwall
Clearing & Grubbing
2 | 201(1) | Clearing & Grubbing | m2 | 184 | 442.8 | 81475.2
Excavation & Backfill
3 | 302(15) | Excavation in unclassified soil and backfill for abutments, and wingwalls. | m3 | 1320 | 3099.61 | 4091485.2
4 | 302(2) | Excavation in highly weathered rock | m3 | 110 | 5313.61 | 584497.1
5 | 302(4) | Excavation in hard rock | m3 | 10 | 7084.81 | 70848.1
6 | 302(9) | Preparation of base for foundation | L.S. | 1 | 885601.63 | 885601.63
7 | 302(10) | Construction of necessary cofferdams cribs sheeting, shoring and bracing and their subsequent removal. | L.S. | 1 | 4428008.17 | 4428008.17 | 147600.27
8 | 302(11) | Dewatering | L.S. | 1 | 1771203.27 | 1771203.27
|  | Concrete For Structures |  |  |  | 0
9 | 1001(1a) | Class A concrete of Grade 30 (20) in foundation slab of abutment and wing wall. | m3 | 175 | 28339.25 | 4959368.75
10 | 1001(1b) | Class A concrete of Grade 30 (20) in abutment and wing walls | m3 | 190 | 26568.05 | 5047929.5
11 | 1001(3a) | Class C concrete of nominal mix 1:3:6(20) as screed under bottom slab of box Bridge & wingwalls. | m3 | 11 | 22140.04 | 243540.44
12 | 1001(1c) | Class A concrete of Grade 25(20) in approach slabs. | m3 | 13 | 24796.85 | 322359.05
13 | 1001(1d) | Class A concrete of Grade 30 (20) in capping beam, ballast wall, curtain walls and bearing pads | m3 | 20 | 26568.05 | 531361
Total Carried Forward | [5 empty] | 38766873.12
Total Brought Forward | [5 empty] | 38766873.12
Formwork
14 | 1008(2) | Rough finish formwork for foundation slabs of abutment and wing walls | m2 | 95 | 2656.8 | 252396
15 | 1008(1a) | Smooth finish formwork for abutment and wingwalls | m2 | 490 | 2656.8 | 1301832
16 | 1008(1b) | Smooth finish formwork for abutment capping beams, ballast walls, curtain walls, bearing pads and approach slabsand wingwalls | m2 | 89 | 2656.8 | 236455.2
Reinforcement
17 | 1002(1a) | Cold worked deformed high yield steel bars of Grade 460 in foundation slabs of abutment and wing walls | M.T. | 14 | 287820.53 | 4029487.42
18 | 1002(1b) | Cold worked deformed high yield steel bars of Grade 460 in abutments and wingwalls | M.T. | 16 | 287820.53 | 4605128.48
19 | 1002(1c) | Hot rolled mild steel bars of Grade 250 in bearing pads corbel and approach slabs. | M.T. | 0.2 | 287820.55 | 57564.11
20 | 1002(1d) | Cold worked deformed high yield steel bars of Grade 460 in abutment capping beams, curtain walls, ballast walls, bearing pads, corbel and approach slabs | M.T. | 2.75 | 287820.53 | 791506.46
|  | Weep Holes |  |  |  | 0
21 | 706(1) | Forming weep holes in abutments & wingwalls using 110mm dia. P.V.C. pipes and finished smooth with dripledge and surround complete as per drawing. | L.m. | 110 | 2214 | 243540
|  | Drainage Backfill Material |  |  |  | 0
22 | 705(1) | 50-200mm. dry stone lining behind abutment & wingwalls as per drawing. | m3 | 25 | 5313.61 | 132840.25
23 | 705(2) | 75mm. thick 40mm. stone filter layer behind dry stone lining as per drawing. | m3 | 4 | 6199.21 | 24796.84
24 | 705(3) | Clay puddled & laid behind abutments & wingwalls to form the impervious layer as per drawing. | m3 | 3 | 3542.41 | 10627.23
Total Carried Forward | [5 empty] | 50453047.11
Total Brought Forward | [5 empty] | 50453047.11
C. SUPER STRUCTURE
Concrete For Structures
1 | 1001(1a) | Infiller concrete of Class A Grade 40(20) between beams in bridge deck inclusive of end make up, screed and camber. | m3 | 90 | 30996.06 | 2789645.4
2 | 1001(1c) | Class A concrete of Grade 25(20) in footwalks and footwalk ramps | m3 | 27 | 24796.85 | 669514.95
Formwork
4 | 1008(1b) | Smooth finish formwork on sides for deck and foot walk concreting | m2 | 60 | 2656.8 | 159408
Reinforcement
5 | 1002(1b) | Hot rolled mild steel bars of Grade 250 intie rods of deck | M.T. | 0.4 | 287820.53 | 115128.21
6 | 1002(1a) | Cold worked deformed high yield steel bars Grade 460 in deck and foot walks. | M.T. | 3.5 | 287820.53 | 1007371.86
Prestressed Concrete
7 | 1003(1) | Pre-tensioned precast concrete beams of cast length 16.5 m supplied as per drawing No. T/B/501A | Nos. | 19 | 309960.57 | 5889250.83
8 | 1003(2) | 16.5m long Pre-tensioned precast concrete beams launched into position as per drawing. | Nos. | 19 | 132840.24 | 2523964.56
Railings
9 | 1018(1) | Precast reinforced concrete railing & uprights in Class A Grade 25(20) concrete inclusive of light reinforcement & mould as per drawing No. T/B/102 A & B. | L.m. | 35 | 22140.04 | 774901.4
10 | 1019(1) | End pillasters in Class A concrete of Grade 25(20) with foundation type II as per drawing No. T/B/513 | Nos. | 4 | 177120.33 | 708481.32
Concrete Kerbs
11 | 807(1) | Precast kerb in Class B Grade 25(20) concrete with light reinforcement & mould as per drawing No. T/B/512 | L.m. | 40 | 3099.61 | 123984.4
12 | 807(4) | Lower kerbs in Class B Grade 20(14) concrete cast insitu as per drawing. | L.m. | 20 | 2656.8 | 53136
Total Carried Forward | [5 empty] | 65267834.04
Total Brought Forward | [5 empty] | 65267834.04
Expansion joints
13 | 1009(1) | Supplying and fixing of mild steel angle iron & hard rubber expansion joint as per drawing No. T/B/107 Rev.1 | L.m. | 20 | 3542.41 | 70848.2
Bridge Bearings
14 | 1010(2) | 75x12mm. hard rubber bearing pads supplied & laid over capping beam and corbel for deck and approach slab as per drawing. | L.m. | 36 | 3542.41 | 127526.76
Miscellaneous
15 | 1012(1) | 20mm Dia. 200mm long stainless steel dowels supplied fixed and grouted at fixed ends as per drawing. | Nos. | 22 | 6642.01 | 146124.22
16 | 1011(1a) | 20mm. Dia.1800mm long hot rolled mild steel dowels driven into bed rock for abutment and wingwalls supplied fixed and grouted as per drawings | Nos. | 20 | 4428.01 | 88560.2
17 | 1011(1b) | 25mm Dia. 200mm long stainless steel dowels supplied fixed and grouted at fixed for approach slabs as per drawing | Nos. | 42 | 7084.81 | 297562.02
18 | 1014(1) | Bituminous sealing felt under approach slabs at capping beam ends to prevent bitumen running on capping beam as per drawing. | L.m. | 22 | 2656.8 | 58449.6
19 | 1016(1d) | Service duct of size 350x230mm. formed in deck as per drawing. | L.m. | 70 | 4428.01 | 309960.7
20 | 1017(1a) | 500x450x75mm. thick paving slabs in Class B Grade 25(20) concrete inclusive of light reinforcement and smooth shuttering provided as per drawing. | Nos. | 35 | 3099.61 | 108486.35
21 | 1017(1b) | 500x450x100m. thick paving slabs in Class B Grade 25(20) concrete inclusive of light reinforcement and smooth shuttering provided as per drawing. | Nos. | 35 | 3542.41 | 123984.35
22 | 806(4b) | 450x450x100mm. thick paving slabs in Class B Grade 25(20) concrete inclusive of light reinforcement and smooth shuttering provided as per drawing. | Sqm | 20 | 6642.01 | 132840.2
23 | 1020(1a) | 110mm. dia. P.V.C. rain water outlets supplied and fixed through deck as per drawing. | Nos. | 12 | 4428.01 | 53136.12
24 | 1020(1c) | 50mm. dia. P.V.C. drain pipes supplied and fixed through deck as per drawing. | Nos. | 6 | 3985.21 | 23911.26
Bill No. 6 Carried to Summary | [5 empty] | 66809224.02